## Sheet1
Modification Logs By Developer
Sr. No. | Title(Requirement) | Date | Modified Tables | Modified Class files | Target Method | Modified by | Order By (On Request on) | Remarks | Reference mail | Tables On Production | Table Modified Date On Prod | Code On Production | Code Deploy Date On Production
1 | Insert createdby and modifiedby in each created and updated APIs. Use T10001 as test userid for Createdby and modifiedby only in Test APK | 22/07/2022 | All POP Table Alterd with Column name (createdby , modifiedby ) | ALL POP Models, POP DAOs And POP Controller | All Methods which Included Createdby and Modifiedby | Juned Baig | Sarang Sir And Adil | DONE |  | YES | 29-07-2022 | YES | 29-07-2022
2 | Allow Trader, Agent and FPO in POP All Service Accesible | 2022-09-08 | No Tables Modified | Only POP DAOs | 1. getLoanQoutesByAcceptedRequest 2.getLogisticsQoutesByAcceptedRequest 3.getSortingQoutesByAcceptedRequest 4.getWinningBidDetails 5.getAssyingRequestByDateAndPlatform 6.getStorageQoutesByAcceptedRequest | Juned Baig | Sarang Sir And Laxminarayan | DONE | Trader login issue in PoP @ Mon, Aug 8, 2022 3:30pm – 4:30pm (GMT+05:30) | No Table Modified |  | YES | 27/03/2023
3 | Add New Parameters in Agri Input Service /rest/get_agri_input_request_list 1. User name 2. User mobile number 3. User location: i. Village ii. Tehsil iii. District iv. State v. GPS co-ordinates 4. Preferred Commodity. | 16/08/2022 | Agri Input request Table (added collumns userstate, userdistrict, usertahsi, uservillage, latitude, longitude, preferredcommodityid, preferredcommodity) | Agri input model, Agri input DAO | 1.getAgriInputRequestList | Juned Baig | Sarang Sir And Adil | DONE | Add parameters in UAT services API | YES | 30-09-2022 | YES | 27/03/2023
4 | Create new Form for Assaying without Lot creation | 23/08/2022 | No Tables Modified | AssayingDao And ConstantQueryApis | AssayingDAO : 1.getAssyingRequestByDateAndPlatform 2.viewAssayingCertificateByLotid ConstantQueryApis : 1.ASSACERTLOT 2.ASSCERTPLATFORMS 3.ASSAREQLISTING | Juned Baig | Sarang Sir And Adil | DONE | Development of new screens for Assaying and Logistics services | No Table Modified |  | YES | 2022-02-11
5 | Issue in POP Dashboard | 21/09/2022 | No Tables Modified | SellerSuppyMstDao And ConstantQueryApis | SellerSuppyMstDao : 1.getSupplyDetailsLocation ConstantQueryApis : 1.SUPPLYCOMMLOV 2.SUPPLYSTATELOV 3.SUPPLYDISTRICTLOV 4.SUPPLYVILLAGELOV | Juned Baig | Sarang Sir And Adil | DONE | Issue in POP Dashboard | No Table Modified |  | YES | 29-09-2022
6 | Add Filter In Get Buyer Demand | 2022-03-11 | No Tables Modified | ConstantQueryApis AND BuyerDemandMstDao | BuyerDemandMstDao : 1.getDemandDetailsByFormToDate ConstantQueryApis : 1.DEMANDSTATELOV 2.DEMANDCOMMOLOV | Juned Baig | Sarang Sir And Adil | DONE | No Mailed | No Table Modified |  | YES | 27/03/2023
7 | POP Enhancement (point 1) : Create API for Service Provider status Response (Trading, Transportation/Logistics, Fiintech/Loan, Storage/Warehouse, Sorting) in Assying just add Reason Column, Agri Advisory | 17/10/22 | Altered Below Tables (poplotentryplatformmstrel, poplogisticsplatformrel, popfinloanplatformmstrel, popstorageplatformrel, popsortingplatformrel) added Collumns (responsefromsp,responsefromspdt,responsereason) (rejectreason column add in poplotsampleassayhdr) | LotEntryHderController And LotEntryheaderDao, LogisticRequestController And LogisticRequestDao, LoanRequestController And LoanRequestDao, SortingRequestcontroller And SortingRequestDao, StorageRequestController And StorageRequestDao | New Method: Name:1.updateServiceProviderStatus (Same Name in All Controller and Dao) | Mayyuresh Gajbhiye | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES Altered Below Tables (poplotentryplatformmstrel, poplogisticsplatformrel, popfinloanplatformmstrel, popstorageplatformrel, popsortingplatformrel) added Collumns (responsefromsp,responsefromspdt,responsereason) (rejectreason column add in poplotsampleassayhdr) | 2023-09-03 | YES | 27/03/2023
8 | POP Enhancement (point 2) : c. After passing bid time, service request is to be closed by system, with remark no bid received. (End After end time +1 hrs.) d. Similarly, in case of advance demand & supply, the information shouldn’t be reflected to the users after passage of expected date & time. | 17/10/22 | No Tables Modified | BidSubmissionController and BidSubmissionDao | Method Name : createTradeDetails ,checkBidCreationByLotidAndBidCreationid | Juned Baig | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | No Table Modified |  | YES | 27/03/2023
9 | POP Enhacement (point 3) Create Assaying Qutes table and Java file for (Assaying Service) | 17/10/22 | New Tables Created for Assaying Qutotes (poplotsampleassayquotes) | Model, Controller, and DAO (MarketInfo) | ALLMethods Created | Juned Baig | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES New Tables Created for Assaying Qutotes (poplotsampleassayquotes) | 2023-09-03 | YES | 27/03/2023
10 | POP Enhacement (point 4) Added new Fields ( Land Size,Village , Tehsil , District, State ) in Agri Advisory | 17/10/22 | ALTERED TABLE popagriadvisoryrequest | AgriAdvisoryRequestModel | getInputAggrigatorQoutesByAcceptedRequest, getUserDetails Created | Juned Baig | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES ALTERED TABLE popagriadvisoryrequest | 2023-09-04 | YES | 27/03/2023
11 | POP Enhacement (point 5) New Service (Market Information) | 17/10/22 | New Tables Created for Market Information (popmarketinforequest, popmarketinforesponse, popmarketinfoplatformrel) | Model, Controller, and DAO (MarketInfo) | ALLMethods Created | Mayyuresh Gajbhiye | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES New Tables Created for Market Information (popmarketinforequest, popmarketinforesponse, popmarketinfoplatformrel) | 2023-09-05 | YES | 27/03/2023
12 | POP Enhacement (point 6) New Service (Institutioal Buyer) | 17/10/22 | New tables Created for Institutional Buyers (popinstitutionalbuyeresponse, popinstitutionalbuyerequest) | Model, Controller, And DAO | ALLMethods Created | Juned Baig | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES New tables Created for Institutional Buyers (popinstitutionalbuyeresponse, popinstitutionalbuyerequest) | 2023-09-06 | YES | 27/03/2023
13 | POP Enhacement (point 7) Create Sub Part of Agri Input (Farm Machinaries and Fertilizers) | 17/10/22 | New tables Created for Agri Input Agregators Sub Menu (popagrifertilizerreq , popagrifarmmachinaryreq) | Model, Controller, and DAO (agri input) | All Methods Created | Mayyuresh Gajbhiye | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES New tables Created for Agri Input Agregators Sub Menu (popagrifertilizerreq , popagrifarmmachinaryreq) | 2023-09-07 | YES | 27/03/2023
14 | POP Enhacement (point 8) Added Fields State, district, tahsil,village, pincode ALL Services | 17/10/22 | ALTER ALL TABLES | ALL POP Models AND POP-DAOs | getByPlatformAndDate() AND getQouteAcceptedRequest() | Juned Baig | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES ALTER ALL TABLES | 2023-09-08 | YES | 27/03/2023
15 | POP Enhacement (point 7) Post Quotes and Quote Consent for Agri Input (Aggregator) | 17/10/23 | New Tables (popagriinputquotes) And Alter popagriinputrequest) | Model , Controller and DAO (Agri Input Quotes) | All Methods Created | Juned Baig | Sarang Sir And Adil | DONE | FW: [WARNING: UNSCANNABLE EXTRACTION FAILED]Changes required in POP. | YES New Tables (popagriinputquotes) And Alter popagriinputrequest) | 2023-09-09 | YES | 27/03/2023
16 | POP Enhacement (point 7) Post Quotes and Quote Consent for Agri Advisory | 2023-09-01 | New Tables (popagriadvisoryquotes) And Altered popagriadvisoryrequest | Model , Controller and DAO (Agri Advisory Quotes) | All Methods Created | Juned Baig | Sarang Sir And Adil | DONE | BRD clarification on Agri Advisory | YES New Tables (popagriadvisoryquotes) And Altered popagriadvisoryrequest | 2023-09-10 | YES | 27/03/2023
17 | Create Combined APIs for Advanced Seller Supply and Buyer Demand Service | 2023-03-01 | No Tables Modified | Model ,Controller and DAO (Buyer Demand , Seller Supply, FetchDataModel) | getCombileDemandData, getCombineSupplyData | Juned Baig | Sarang Sir And Adil | DONE | W: Invitation: Advance Demand & Supply @ Thu Nov 24, 2022 12pm - 1pm (IST) (chiranjiv.s@ikisan.com) | No Table Modified |  | YES | 2023-09-01
18 | Create APIs for Other Services | 13/01/2023 | New Tables Created (popotherservicerequest, popotherservicequotes, popotherserviceplatformrel) | Model , Controller and DAO (Other Services ) | ALL Methods Created | Juned Baig | Sarang Sir And Adil | DONE | Regarding Other categories- POP | YES Table Modified (poplogisticrequest, poplogisticquotes) | 2023-09-10 | YES | 27/03/2023
19 | Modifications in Logistics/Transportation Added new Field for Commodity variety in logistic Request and Handling Charges in Logistic Quote table | 17/01/2023 | Table Modified (poplogisticrequest, poplogisticquotes) | Model and DAO | Create And Get Method Modified | Juned Baig | Sarang Sir And Adil | DONE | FW: PoP new report format | YES Table Modified (poplogisticrequest, poplogisticquotes) | 19-01-2023 | YES | 27/03/2023
20 | Adil's 9 Points (1. No front end screen available to view requests & Status raised by user in the enam application. ) | 24/01/23 | No Tables Modified | ConstantQueryApis | Create new APIs LOTACCEPPLATFORM, ASSAACCEPLATFORM LOGIACCEPLATFORM, LOANACCEPLATFORM, STORACCEPLATFORM, SORTACCEPLATFORM, AGRIACCEPLATFORM, INPUACCEPLATFORM, MRKTACCEPLATFORM, OTHRACCEPLATFORM | Juned Baig | Sarang Sir And Adil | DONE | FW: POP Module - Staging APK | No Table Modified |  | YES | 27/03/2023
21 | Validations on third party access APIs | 2023-06-03 | No Tables Modified | All Controller and DAO | Update_sp_status, post_quotes, Post_status | Juned Baig | Sarang Sir And Adil | DONE | Re: Re[2]: POP Platform Ids | No Table Modified |  | YES | 27/03/2023
22 | Create A new API for get Assaying Qoute Accepted data | 21/03/2023 | No Tables Modified | AssayingDao and AssayingController | getAcceptedAssayingRequest | Juned Baig | Shalaka And Adil | DONE | Re: Re[2]: issue in POP Assaying API | No Table Modified |  | YES | 27/03/2023
23 | Added new Columns in Institutional Buyers Request | 2023-03-04 | Alter popinstitutionalbuyerequest | InstitutionalBuyerRequestController , InstitutionalBuyerRequestDao | crud , updateInstitutionalBuyersConsent | Juned Baig | Sarang Sir And Adil | DONE | API are not as per requirement shared for Institutional Buyers | YES Table Modified (popinstitutionalbuyerequest) | 2023-10-04 | YES | 20/03/2023